## Sheet1
| Milestone Plan |  |  |  | Team Development | Team Member | Start | End | Skills Targetted |  | Actions
Ti | Task 1 Identify Team Members | Laura | 2022-01-20 | 2022-01-23 | Research Git / Github | Luke Citrine | 2022-01-21 | 2022-01-24 | Planning |  | Obtain dataset
T2 | Task 2 Establish Skill Baseline | Laura | 2022-01-21 | 2022-01-23 | Deliver Git / Github overview to team | Luke Citrine | 2022-01-25 | 2022-01-25 | Communication | Presenting | Review dataset
T3 | Task 3 Agree & Plan Role Rotation | Laura | 2022-01-20 | 2022-01-25 | Research Python | Luke Curren | 2022-01-21 | 2022-01-24 | Planning |  | Dataset - fit for purpose review
D1 | Task 4 Search for suitable crime data | Team | 2022-01-21 | 2022-01-25 | Deliver overview to team | Luke Curren | 2022-01-25 | 2022-01-25 | Communication | Presenting | Accept or search for different set
D2 | Task 4a Review data suitability | Team | 2022-01-20 | 2022-01-25 | Review Rubric | Shane | 2022-01-21 | 2022-01-24 | Planning |  | Review & demonstate Git / Github
D3 | Task 4 Agree Data Set | Laura | 2022-01-25 | 2022-01-30 | Deliver overview to team | Shane | 2022-01-25 | 2022-01-25 | Communication | Presenting | Review & demonstate Python
D4 | Task 5 Determine Project Outline | Laura | 2022-02-25 | 2022-02-01 | Support team | Cameron | 2022-01-21 | 2022-01-25 | Teamwork | Communication | Review & share important marking criteria
R1 | Review & demonstate Git / Github | Luke Citrine | 2022-01-21 | 2022-01-25 | Support team | Laura | 2022-01-21 | 2022-01-25 | Teamwork | Communication
R2 | Review & demonstate Python | Luke Crren | 2022-01-21 | 2022-01-25 | Support team | Niamh | 2022-01-21 | 2022-01-25 | Teamwork | Communication
R3 | Review & share important marking criteria | Shane | 2022-01-21 | 2022-01-25