## Tasks
# | Assignment Tasks | Person | Date Started | Date Finished | Skills targeted | Data Analysis
A | Team |  |  |  |  | Communication
A1 | Identify people in the team. | ALL | Thu 20 Jan 2022 | Sun 23 Jan 2022 | Communication | Maths
A2 | Identify Skillset of people in team. | ALL | Fri 21 Jan 2022 | Sun 23 Jan 2022 | Planning/Communication | Planning
A3 | Learning Log/Agree on Plan Role Rotation | ALL | Thu 20 Jan 2022 | Tue 25 Jan 2022 | Planning/Communication | Presenting
B | GitHub |  |  |  |  | progress
B1 | Team/Accounts created | ALL | Thu 20 Jan 2022 | Sun 23 Jan 2022 | Planning | Teamwork
B2 | Add team to GitHub | ALL | Thu 20 Jan 2022 | Sun 23 Jan 2022 | Planning
B3 | Check Access to all users. | Luke | Thu 20 Jan 2022 | Sun 23 Jan 2022 | Planning
C | Project Pre-Start
C1 | Identify Team/Skills/Access | ALL | Fri 21 Jan 2022 | Sun 23 Jan 2022 | Communication/Progress
C2 | Identify potential data | Niamh | Fri 21 Jan 2022 | Sun 23 Jan 2022 | Data Analysis
C3 | Ready Data | Laura | Mon 25 Jan 2022 | Mon 25 Jan 2022 | Data Analysis
C4 | Distrubute Table Data Across the Team | ALL | Mon 25 Jan 2022 | Mon 25 Jan 2022 | Communication
C5 | Obtain GitHub/Python Skills | ALL | Mon 25 Jan 2022 | Mon 25 Jan 2022 | Data Analysis
C6 | Simple outline of the Marking Criteria/Rubrib | Shane | Mon 25 Jan 2022 | Mon 25 Jan 2022 | Planning
C7 | Simple outline of the Specifications Document | Niamh | Mon 25 Jan 2022 | Mon 25 Jan 2022 | Planning
D | Project Start
D1 | Review data sustainability | Laura | Mon 25 Jan 2022 | Tue 1 Feb 2022 | Data Analysis
D2 | Identify trends in the data | Niamh | Mon 25 Jan 2022 | Tue 1 Feb 2022 | Data Analysis
D3 | Agree on Data Analysis stratigy | ALL | Mon 25 Jan 2022 | Tue 1 Feb 2022 | Communication/Data Analysis
D4 | Dertermine Project Outline | Luke | Mon 25 Jan 2022 | Tue 1 Feb 2022 | Progress
D5 | Determine columns to be aligned and how | ALL | Mon 25 Jan 2022 | Mon 25 Jan 2022 | Progress
D6 | Identify Algorithms based on Analysis statigy | ALL | Mon 25 Jan 2022 | Mon 25 Jan 2022 | Communication/Progress
D7 | Using Outline of Specification doc - Create Doc | ALL | Mon 25 Jan 2022 | Mon 25 Jan 2022 | Communication/Progress
E | Coding and Algorithms
E1 | Implement Algorithm(s) based on Analysis | ALL | Mon 25 Jan 2022 | Mon 25 Jan 2022 | Data Analysis
E2 | Optimize Algorithm(s) if needed | ALL | Mon 25 Jan 2022 | Mon 25 Jan 2022 | Data Analysis